## Sheet1
Sl No | Milestones | Additional Instruction | Status | Completed Date | Target Date | Comments if any
1 | Data Collection | 1. For GraphRAG Knowledge Graph •Gather cybersecurity articles, reports, and whitepapers from trusted sources. 2. For Fine-Tuning a Model •Extract Q&A pairs from cybersecurity podcasts, blogs, and conference transcripts. •Save extracted Q&A paires into scv file for fine-tuning. | completed | 29:08 | 29:08
2 | RAG Integration | • Vector layer: Embed CTI chunks + entity summaries into LanceDB. • Graph layer: Build/ingest CTI knowledge graph (ATT&CK objects + linked entities) for Microsoft GraphRAG neighborhood-aware retrieval. | in progress |  | 19:09
3 | Dialogue Generation Fine-Tuning | • Base Model: Choose a strong open-source LLM (Mistral, LLaMA 3, Phi-3, or similar). • Fine-Tuning Objective: o Train on curated cybersecurity Q&A pairs to emulate an analyst-to-analyst advisory tone. o Include scenario-based responses (incident triage, threat attribution, mitigation recommendations). o Preserve domain accuracy and ensure answers remain grounded when combined with RAG outputs. • Method: o LoRA or QLoRA for parameter-efficient fine-tuning. o Validation on unseen Q&A + adversarial red-teaming to check factual consistency. |  |  | 25:09
4 | Orchestration | Use LangChain or Semantic Kernel for chaining: query parsing → entity/intent detection → graph/vector retrieval → re-ranking → summarization → dialogue generation. |  |  | 3:10
5 | User Interface | • Backend: FastAPI (suggestion) • Frontend: Streamlit |  |  | 10:10
6 | Example Workflows | Query: "What’s the latest on ALPHV targeting healthcare in Europe?" • Retrieve reports (CERT-EU, ENISA, vendor intelligence). • Graph expansion → relevant TTPs, tools, CVEs. • Summarize & respond via fine-tuned dialogue model with analyst-style commentary. Query: "Compare Scattered Spider and Lapsus$ initial access methods." • Retrieve & compare via ATT&CK techniques. • Return side-by-side analysis with citations and security recommendations. |  |  | 17:10
7 | Writing the thesis |  |  |  | 7:11
8
9
10
11
12
13
14
15